## Management Summary
| Total |  |  | Coding |  |  | Meetings |  |  | Systems Analysis |  |  | Overhead
| Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit
Shubham | 4000 | #REF! | #REF! | 0 | 0 | 0 | 1000 | #REF! | #REF! | 0 | 0 | 0 | 3000 | 0 | 3000
Sam | 4000 | #REF! | #REF! | 0 | 0 | 0 | 1000 | #REF! | #REF! | 0 | 0 | 0 | 3000 | 0 | 3000
Upal | 4000 | #REF! | #REF! | 0 | 0 | 0 | 1000 | #REF! | #REF! | 0 | 0 | 0 | 3000 | 0 | 3000
Jishnu | 4000 | #REF! | #REF! | 0 | 0 | 0 | 1000 | #REF! | #REF! | 0 | 0 | 0 | 3000 | 0 | 3000
Owen | 7900 | #REF! | #REF! | 3200 | 0 | 3200 | 1000 | #REF! | #REF! | 700 | 1400 | -700 | 3000 | 0 | 3000
Lalith | 4000 | #REF! | #REF! | 0 | 0 | 0 | 1000 | #REF! | #REF! | 0 | 0 | 0 | 3000 | 0 | 3000
Nikki
Total | 27900 | #REF! | #REF! | 3200 | 0 | 3200 | 6000 | #REF! | #REF! | 700 | 1400 | -700 | 18000 | 0 | 18000

## Gantt
| predicted time(hrs) | time spent(hrs) | Status | key | complete | this week | planned
Shubham |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59
Task 1 | 0 | 0 | planned
Task 2 | 0 | 0 | planned
totals | 0 | 0
Sam
Task 1 | 0 | 0 | planned
Task 2 | 0 | 0 | planned
totals | 0 | 0
Upal
Task 1 | 0 | 0 | planned
Task 2 | 0 | 0 | planned
totals | 0 | 0
Jishnu
Task 1 | 0 | 0 | planned
Task 2 | 0 | 0 | planned
totals | 0 | 0
Owen
Initial Research/Brainstorming | 2 | 0 | planned | bar: key 1 to complete 2
HUD Menu Design | 1 | 0 | planned | bar: this week 3 to planned 8
Database Construction For HUD | 2 | 0 | planned | bar: this week 3 to planned 4
Documentation | 4 | 0 | planned | bar: planned 5 to planned 23
Program HUD Menu | 2 | 0 | planned | bar: planned 9 to planned 10
Research/Brainstorming For Inventory & Clues | 3 | 0 | planned | bar: planned 11 to planned 13
Inventory Design | 1 | 0 | planned | bar: planned 11 to planned 13
Program Inventory | 2 | 0 | planned | bar: planned 14 to planned 15
Clue Design | 1 | 0 | planned | bar: planned 11 to planned 13
Program Clues | 1 | 0 | planned | bar: planned 14 to planned 15
Research/Brainstorming For Settings | 2 | 0 | planned | bar: planned 11 to planned 12
Settings Design | 1 | 0 | planned | bar: planned 11 to planned 12
Program Settings | 2 | 0 | planned | bar: planned 13 to planned 15
Link Components | 1 | 0 | planned | bar: planned 16
Testing | 6 | 0 | planned | bar: planned 17 to planned 22
Installation | 1 | 0 | planned | bar: planned 23
totals | 32 | 0
Lalith
Task 1 | 0 | 0 | planned
Task 2 | 0 | 0 | planned
totals | 0 | 0
Nikki
Task 1 | 0 | 0 | planned
Task 2 | 0 | 0 | planned
totals | 0 | 0
group totals (hrs) | 32 | 0
group totals ($) | 3200 | 0

## Team Mate Delverables
TL 1 Deliverables |  |  | TL 2 Deliverables |  |  | TL 3 Deliverables |  | TL 4 Deliverables | TL 5 Deliverables | TL 6 Deliverables
Date Due: 2/27 |  |  | Date Due: 2/29 |  |  | Date Due: 3/21 |  | Date Due: 3/26 & 3/28 | Date Due: 4/4 | Date Due: 4/7 & 4/9
By Tuesday 2/27: Initial Readme File in GIT |  |  | By Thursday 2/29: Initial function in GIT that the MVP can call |  |  | By Thurday 3/21: Submit to GIT: 2 Boundary Tests 1 Stress Test |  | By Monday 3/26: | By Monday 4/4@6pm: | By Thursday 4/7:
[8 empty] | 1. Fully update your sections of the Gantt chart | 1: Update the gantt for what you have worked on.
2: Send me an update on what you have been working on this week.
By Wednesday 3/26:
1. Look over the coding standards in the GIT
2. Try to update your code to comply with the coding standards (to the best of your ability, BC is not expecting it to be perfect). Message me when you're done and I'll check you off.
Location: |  |  | Location: |  |  | Location: |  | Location: | Location: | Location:
Get deliverables to TL by 6pm on Date Due
Deliverable Tracker
| Shubham | Sam | Upal | Jishnu | Owen | Lalith | Nikki
TL 1 | ü | ü | ü | ü | ü | ü | ü
TL 2 | ü | ü | ü | ü | ü | ü | ü
TL 3 | ü | ü | ü | ü | ü | ü | ü
TL 4 | ü | ü | ü | ü | ü | ü | ü
TL 5 | ü | ü | ü | ü | ü | ü | ü
TL 6 | ü | ü | ü |  | ü | ü | ü

## Meetings
ü

## SA
| Task | Predicted(hrs) | spent(hrs) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Shubham | Individual schedule | 0 | 0
| Champion | 0 | 0
| Subtotal | 0 | 0
Sam | Individual schedule | 0 | 0
| Champion | 0 | 0
| Subtotal | 0 | 0
Jishnu | Individual schedule | 0 | 0
| Champion | 0 | 0
| Assemble SA Powerpoint | 0 | 0 | bar: 10
| Subtotal | 0 | 0
Upal | Individual schedule | 0 | 0
| Champion | 0 | 0
| Subtotal | 0 | 0
Owen | Individual schedule | 0 | 0
| Champion | 7 | 14
| Subtotal | 7 | 14
Lalith | Individual schedule | 0 | 0
| Champion | 0 | 0
| Subtotal | 0 | 0
Nikki | Individual schedule | 0 | 0
| Champion | 0 | 0
| Subtotal | 0 | 0
| Total | 7 | 14

## Overhead
| Shubham | Sam | Upal | Jishnu | Owen | Lalith | Nikki
Training | 0 | 0 | 0 | 0 | 0 | 0 | 0
SA Preesentation Prep | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software Specialist Presnetaion Prep | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team Lead Presentation Prep | 0 | 0 | 0 | 0 | 0 | 0 | 0
Oral Exam Prep | 0 | 0 | 0 | 0 | 0 | 0 | 0
Post Mortum Presentation Prep | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0